## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Students Analysis |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Harshada Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2024-08-30 | Data Gathering procedure | Requirements Gathering | NO | Collected data through google forms than manually | Created a Google form to collect data | self | Solved | Null
2 | 2024-09-01 | Designing Data Set | Design | NO | Arranged data in order of income | Filtered the income data | self | Solved | Null
3 | 2024-09-03 | Visuals issue | Development | NO | Arranged Visuals in the related topic | Corrected the dashboard | self | Solved | Null
4 | 2024-09-06 | Communication Issue | Communication Findings | NO | Arranged Results in Meaningful order | Arranged Results correctly | self | Solved | Null